## PM
Sun Pool Manager Project Schedule
| Project Start Date | 2024-01-02 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Anas Alseid | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19
 | time axis 2024-01-01 to 2024-02-25
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-01-01 to 2024-02-25
1 | Project Planning |  |  |  | - |  |  | -
1.1 | Project Scope | Yazeed Mwafi |  | Wed 3/06/24 | Wed 3/20/24 | 2 | 100% | 14
1.2 | Project Objectives | Laith Jaber |  | 2024-01-04 | 2024-01-06 | 2 | 100% | 2
2 | Requirments and anlysis | [6 empty] | -
2.1 | Functional Requirments | Yazeed Mwafi |  | Thu 3/21/24 | Thu 3/28/24 | 8 | 100% | 8
2.2 | Non-functional Requirmnats | Alass Al-Hmoud |  | Thu 3/21/24 | Wed 3/27/24 | 7 | 100% | 7
3 | Architicture and Design | [6 empty] | -
3.1 | Use case diagram | Alaa Al-Hmoud |  | Thu3/28/24 | Wed 4/03/24 | 7 | 100% | 7
3.2 | Use case flow-of-events | Laith Jaber |  | Thu 4/04/24 | Wed 4/10/24 | 7 | 100% | 7
3.3 | Class diagram | Laith Jaber |  | Thu 4/11/24 | Wed 4/17/24 | 7 | 100% | 7
3.4 | Enity relationship diagram | Yazeed Mwafi, Laith Jaber |  | 2024-02-09 | 2024-02-12 | 4 | 100% | 2
3.5 | Testing and Validation | Yazeed Mwafi, Alaa Al-Hmoud |  | 2024-02-13 | 2024-02-15 | 3 | 100% | 3
4 | Implementation & Testing | [6 empty] | -
4.1 | User Interface Implementation | Yazeed Mwafi, Laith Jaber |  | Mon 7/15/24 | Tue 7/30/24 | 15 | 100% | 15
4.2 | Database Implementation | Yazeed Mwafi, Laith Jaber |  | Wed 7/31/24 | Tue 8/13/24 | 14 | 100% | 14
4.3 | Backend Functionality Implementation | Yazeed Mwafi, Laith Jaber |  | Wed 8/14/24 | Tue 8/27/24 | 14 | 100% | 14
4.4 | Final Integration and Testing | Yazeed Mwafi, Laith Jaber |  | Wed 8/28/24 | Sat 8/31/24 | 4 | 100% | 4
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Risk Register
ID | Risk Description | Category | Impact | Mitigation Plan | Contingency Plan | Owner
1 | Sensor malfunction due to environmental conditions | Technical | High | Use high-quality, weather-resistant sensors. Implement regular maintenance and calibration checks. | Keep spare sensors available for quick replacement. | Project Manager
2 | Delay in hardware procurement | Schedule | Medium | Source multiple suppliers and order hardware well in advance. | Use alternative components if possible. | Procurement
3 | Data security breach | Security | High | Implement strong encryption and access control measures. Regularly update and patch software. | Have a robust incident response plan in place. | Security Lead
4 | Integration issues between IoT devices and Flutter app | Technical | High | Conduct thorough integration testing and use established protocols. | Allocate additional time and resources for troubleshooting. | Development Team
5 | Power supply failure | Technical | High | Use a reliable solar power system with battery backups. | Have a backup power source available. | Technical Lead
6 | AI algorithm inaccuracies | Technical | Medium | Continuously train and validate AI models with diverse datasets. | Implement manual override options for critical operations. | AI Team
7 | User resistance to adopting new technology | Organizational | Medium | Provide comprehensive training and support to users. | Gather user feedback and address concerns promptly. | Change Manager
8 | Budget overrun | Financial | High | Regularly monitor and review budget. Implement cost-saving measures. | Reallocate funds from less critical areas if necessary. | Financial Officer
9 | Regulatory compliance issues | Legal | High | Ensure all aspects of the project comply with relevant regulations. Consult legal experts if needed. | Prepare to make necessary adjustments to comply with regulations. | Compliance Officer
10 | Insufficient project resources | Resource | High | Plan resource allocation carefully and ensure team members have the required skills. | Hire additional resources or reallocate existing ones as needed. | Resource Manager
11 | Inaccurate sensor readings | Technical | Medium | Use sensors with high accuracy and reliability. Perform regular calibration and validation. | Implement software filters and error-checking algorithms. | Technical Lead
12 | Communication breakdown within the project team | Organizational | Medium | Foster open communication channels and regular meetings. Use collaboration tools effectively. | Escalate issues to higher management if unresolved. | Project Manager